## Status tracker
Task ID | Task Name | Description | Estimation in hours | Actual hours | Status | Owner | Comments | Completed date
1 | Create Dashboard | This involves creating Project Structure and aslo implement junit test cases and consume web services to send request and get response | 24 | 18 | Completed | Naga Busa | Completed static view of DashBoard and Dining Page and project structure. | 24/01/2017
| create book dinning and dinning confirmation pages. | Solved the issue regarding datepicker and consumed web services to get reponse. | 24 | 12 | Completed | Naga Busa | Solved the issue regarding datepicker and consumed web services to get response | 24/01/2017
2 | Create master GitHub repository |  | 2 | 1 | Completed | Aakash Verma | Another 1 repository is yet to be created for UI | 24/01/2017
3 | Create Guest registration page. | To build project structure.Create Guest registration page on adding angular js validations,and to perform junit testing to obtain code coverage, consume web services to send request and get response. | 24 | 12 | Completed | Sukirta SR | Completed registration page with validations for all input fields on angular js and project structure.completed registration with service integration. | 24/01/2017
10 | Create View iternary page | view iternary page inorder to display the booking and cancelling and to perform junit testing to obtain code coverage, consume web services to send request and get response. | 24 | 12 | Completed | Sukirta SR | Completed static view iternary page. Waiting for the service to integrate. Working on itinerary service integration | 24/01/2017
6 | Service:- Book Resort Reservation | This task includes implementation of Book Resort Reservatio restful service, implement Junits having 80% code coverage, zero checkstyle and PMD violations. | 27 | 18 | Completed | Alok Kumar | Completed implementaion of Book Resort Reservation restful service. Junit Completed. | 24/01/2017
7 | Service:- Provide Resort Reservations by Guest ID | This task includes implementation of Provide Resort Reservations by Guest ID restful service, implement Junits having 80% code coverage,zero checkstyle and PMD violations | 18 | 9 | Completed | Alok Kumar | Completed implementaion of Provide Resort Reservations by Guest ID. Junit completed. | 24/01/2017
8 | Service:- Cancel Resort Reservation | This task includes implementation of Cancel Resort Reservation restful service, implement Junits having 80% code coverage,zero checkstyle and PMD violations | 9 | 7 | Completed | Alok Kumar | Completed implementaion of Cancel Resort Reservation. Write code for createdDate and updatedDate. Junit completed. | 24/01/2017
9 | Implement "Show Itinerary"RESTful service | This task includes implementation of show itinerary restful service, implement Junits having 80% code coverage, zero checkstyle and PMD violations. | 50 | 18 | Completed | Deepika RK | Completed implemenation of show itinerary restful service Junit completed. | 24/01/2017
11 | Service:-Validateguest | This task includes implementation of Validateguest restful service, implement Junits having 80% code coverage,zero checkstyle and PMD violations | 24 | 10 | Completed | Naina Dubey | Completed implementaion of Validateguest restful service . Junit completed. | 24/01/2017
5 | Service:- Createguest | This task includes implementation of Create Guest restful service, implement Junits having 80% code coverage, zero checkstyle and PMD violations. | 27 | 18 | Completed | Naina Dubey | Completed implementaion of create guest restful service. Completed implementaion of validate guest restful service. Junit completed. | 24/01/2017
11 | Service:- Book Dining Reservation | This task includes implementation of Book Dining Reservatio restful service, implement Junits having 80% code coverage, zero checkstyle and PMD violations. | 27 | 18 | Completed | Sonu Kumar Sah | Completed implementaion of Book Dining Reservation restful service. Junit completed. | 24/01/2017
12 | Service:- Provide Dining Reservations by Guest ID | This task includes implementation of Provide Dining Reservations by Guest ID restful service, implement Junits having 80% code coverage,zero checkstyle and PMD violations | 18 | 9 | Completed | Sonu Kumar Sah | Completed implementaion of Provide Dining Reservations by Guest ID. Junit completed. | 24/01/2017
13 | Service:- Cancel Dining Reservation | This task includes implementation of Cancel DiningReservation restful service, implement Junits having 80% code coverage,zero checkstyle and PMD violations | 9 | 7 | Completed | Sonu Kumar Sah | Completed implementaion of Cancel DiningReservation. Junit completed. | 24/01/2017
14 | create Book resort and book resort confirmation pages. | This involves creating a book resort and book resort confirmation static pages,consume the web services ,mapping it to my page,write junit test cases for obtaining 80%code coverage. | 24 | 12 | Completed | Pavithra K | Created static book resort and book resort confirmation pages but should add a date calculator in book resort page. Added datepicker but calculating the number of nights is pending, attend KT on how to consume webservices. | 24/01/2017
4 | Build project structure,create login page. | This task invloves creating the project structure ,create static login,provide angularjs validations,implement junit test cases for having 80% code coverage,consume webservices to send request and obtain response | 24 | 12 | Completed | Pavithra K | completed static login page,angularjs validation done for the email and password in login page,created project structure worked on providing webservices for login page. Completed providing webservices for loginpage. | 24/01/2017

## Issues
Issue ID | Issue Description | owner | assigned to | Priority | status | Issue Date | Resolve By date | Comments
1 | Date calculator | Pavithra | Pavithra | High | Closed | 2017-03-01
2 | Cursor position on reset | Sukirta | Sukirta | High | Closed | 2017-03-01
3 | Time picker | Mahesh | Mahesh | High | Closed | 2017-05-01

## Risks
Risk ID | Risk Description | owner | assigned to | Priority | status | Resolve By date | Comments